## Directions
User story writing directions | Possible bids | Value in hours | Possible User story States
Step 1: Features | A | 2 | On Hold
Receive features from your AP about what feature absolutely must be completed by the end of the sprint | 2 | 4 | Sprint Backlog
Review the features and evaluate if there are any other features you feel should be tackled during the sprint | 3 | 8 | In Progress
| 5 | 12 | Complete
Step 2: Stories | 8 | 16
Break the features apart into deliverable tasks | J | 40
write a user story for each one of those tasks | Q | 80
write a list of test cases for each of the user stories | K | OMGWTFBBQ
Bidding Directions
Step 1: Bidding
Each person evaluates how difficult the task is without bias from other members.
They will represent that difficulty by how long they estimate the task will take to complete.
Each team member will pick which of the possible bids best represents how difficult they evaluate the task to be
Step 2: Negotiation
The team must have a consensus on how difficult the task is
Each team member reveals what bid they decided upon on the previous step
If there is a differing of bids the team must discuss why the bids differ and must come to an agreement on the tasks value
Step 3: Allocation
After every user story has been bided and have had all their values agreed upon the user stories must be assigned owners.
Generally the owner of a task should be the person that bided the lowest on that task.
Once all of the tasks have been assigned owners tally up the total value of each persons tasks
If the distribution of tasks is not even rebalance the tasks owners until it is.

## Team info
Team Name
The team | Team Homeless Titans
Team Members | Phone # | Email
Charles Stoll | 561-239-2046 | notserp007@gmail.com
Daniel Makin | 607-345-1638 | dpmakin@gmail.com
Nick Kemner | 610-310-5632 | tabu34@gmail.com
Wheel spins
First well
Second wheel
Third wheel

## S1 Allocation
Sprint 1 Allocation |  | Bids | [5 empty] | Finals
User Stories |  | Charles Stoll | Daniel Makin | Nick Kemner | 0 | 0 | 0 | Agreed upon bid | Owner
As a team member, I want to get our game idea approved and accepted
As a team member, I want to know all of the contact information for my team mates
As a team, we want to generate a one page summary of our game idea
As a team member, I want to create a feature list for our game. |  | 2 | 2 | 2 | 2 |  |  | 2 | Charles Stoll
As a team, we want to have SVN running
As a programmer, I want to build UML diagrams of the game architecture and export if to a HTML file |  | 2 | 2 | 2 | 2 |  |  | 2 | Daniel Makin
As a team member, I want to document the design of our game in its entirety |  | 4 | 4 | 4 | 4 |  |  | 4 | Nick Kemner
As a team member, I want to design the interface for the game through pictures |  | 2 | 2 | 2 | 2 |  |  | 2 | Charles Stoll
As a team member, I want to document the Asset dependencies |  | 4 | 4 | 4 | 4 |  |  | 4 | Manuel Diaz
As a programmer, I want to document Preexisting Technology |  | 2 | 2 | 2 | 2 |  |  | 2 | Charles Stoll
As a team member, I want to design particle editor Tool |  | 4 | 4 | 4 | 4 |  |  | 4 | Manuel Diaz
As a team member, I want to design animation editor Tool |  | 4 | 4 | 4 | 4 |  |  | 4 | Charles Stoll
As a team member, I want to design tile editor Tool |  | 4 | 4 | 4 | 4 |  |  | 4 | Nick Kemner
As a team member, I want to assemble the documentation for SGP including the Game Proposal, Feature List, Tools doc, Preexisting technology, Asset dependencies, and UML diagram |  | 2 | 2 | 2 | 2 |  |  | 2 | Daniel Makin
As a programmer, I want to set up the base game hierarchy consisting of directX up and running and main game objects rendered with basic functionality |  | 4 | 4 | 4 | 4 |  |  | 4 | Daniel Makin
You must insert rows above this point when adding user stories
Totals
|  | Charles Stoll | Daniel Makin | Nick Kemner | 0 | 0 | 0 | Totals
|  | 10 | 8 | 8 | 0 | 0 | 0 | 34
User Stories | Priority | Test cases
As a team member, I want to get our game idea approved and accepted | high
Does our idea meet the scope of the class?
Has our idea been approved by the Associate producers?
Has our idea been approved by the Executive producers?
As a team member, I want to know all of the contact information for my team mates | medium
Do we have each team members email?
Do we have each team members phone number?
Have we agreed upon a time that we are going to meet to work on the project?
As a team, we want to generate a one page summary of our game idea | medium
Can we accurately describe our game in the time it would take to ride an elevator?
Have we listed out the major features of the game?
As a team member, I want to create a feature list for our game. | high
Do we have a list of ever feature we are going to need to produce this game?
As a team, we want to have SVN running | medium
Do we have a SVN repository set up?
Do we have SVN installed on each team members computer?
Can each team member update and commit to the repository?
As a programmer, I want to build UML diagrams of the game architecture and export if to a HTML file | high
Have we diagramed the classes we are going to need to make this game in UML?
Have we documented the methods of those classes in UML?
Have we added comments under the Documentation field in UML do describe what the classes and methods are going to be used for?
Have we set up relationships for the classes in UML?
Have we exported the document into an HTML file
As a team member, I want to document the design of our game in its entirety | high
Does our documents properly describe how the game plays?
Does our document describe all of the game objects?
Does our game describe the AI patterns represented in the game?
Does our document use factual numbers to represent values and statistics?
Does our document describe what style of art music and sounds our game is going to use?
Does our document describe all of the levels/zones/locations in the game?
Does our document describe everything that is in OUR game?
As a team member, I want to design the interface for the game through pictures | medium
Do we have every screen that is going to be in the game listed?
Do we have a flow chart for the screens in the game?
Do we have each screen laid out with explanations of the screens functionality and content?
As a team member, I want to document the Asset dependencies | low
Do we have a list of each animation we are going to need for the game?
Do we have a list of each particle effect we are going to need for the game?
Do we have a list of each tile image we are going to need to make the levels?
As a programmer, I want to document Preexisting Technology | medium
Do we have a list of all the pre existing code or tools we are going to use to produce this game?
As a team member, I want to design particle editor tool | medium
Do we have a short description of what the tool will be used for?
Do we have the interface with all the requirements of the editor laid out?
Do we have a key describing the functionality of the tools features?
As a team member, I want to design animation editor tool | medium
Do we have a short description of what the tool will be used for?
Do we have the interface with all the requirements of the editor laid out?
Do we have a key describing the functionality of the tools features?
As a team member, I want to design tile editor tool | medium
Do we have a short description of what the tool will be used for?
Do we have the interface with all the requirements of the editor laid out?
Do we have a key describing the functionality of the tools features?
As a team member, I want to assemble the documentation for SGP including the Game Proposal, Feature List, Tools doc, Preexisting technology, Asset dependencies, and UML diagram | medium
Have we assembled all the documentation (other that the code architecture html) into a single one note file?
Have we organized the one note file to allow people to find information easily?
As a programmer, I want to set up the base game hierarchy consisting of directX up and running and main game objects rendered with basic functionality | medium
Do we have the base hierarchy of out game set up?
Do we have our main game objects represented in some way?
Can we interact with the main game objects?

## S2 Allocation
Sprint 2 Allocation |  | Bids | [5 empty] | Finals
User Stories |  | Charles Stoll | Daniel Makin | Nick Kemner | 0 | 0 | 0 | Agreed upon bid | Owner
As an artist, I want a well thought-out and usable interface for my Animation editor. |  | 4 | 4 | 4 | 4 |  |  | 4 | Charles Stoll
As a designer, I want the buttons and tools in the Animation editor to be functional and my editor to fulfill the requirements of the class. |  | 8 | 8 | 8 | 8 |  |  | 8 | Charles Stoll
As a developer, I want my animation editor to be able to save and load my animations using relative paths. |  | 4 | 2 | 4 | 2 |  |  | 4 | Charles Stoll
As a developer, I want an In-Tool engine to be able to render the animation that I am working with. |  | 2 | 2 | 2 | 2 |  |  | 2 | Charles Stoll
As a programmer, I want to be able to load the assets created from the animation editor as well as any files needed for said asset. |  | 4 | 2 | 4 | 4 |  |  | 4 | Charles Stoll
As an artist, I want a well thought-out and usable interface for my world editor. |  | 4 | 4 | 4 | 4 |  |  | 4 | Nick Kemner
As a designer, I want the buttons and tools in the world editor to be functional and my editor to fulfill the requirements of the class. |  | 12 | 8 | 8 | 12 |  |  | 12 | Nick Kemner
As a developer, I want my world editor to be able to save and load my maps using relative paths. |  | 4 | 2 | 4 | 2 |  |  | 4 | Nick Kemner
As a developer, I want an In-Tool engine to be able to render the map that I am working with. |  | 2 | 2 | 2 | 2 |  |  | 2 | Nick Kemner
As a programmer, I want to be able to load the assets created from the world editor as well as any files needed for said assets. |  | 4 | 4 | 4 | 4 |  |  | 4 | Nick Kemner
As an artist, I want a well thought-out and usable interface for my particle editor. |  | 4 | 4 | 4 | 4 |  |  | 4 | Manuel Diaz
As a designer, I want the buttons and tools in the particle editor to be functional and my editor to fulfill the requirements of the class. |  | 8 | 8 | 8 | 12 |  |  | 8 | Manuel Diaz
As a developer, I want my particle editor to be able to save and load my particles using relative paths. |  | 4 | 2 | 4 | 4 |  |  | 4 | Manuel Diaz
As a developer, I want an In-Tool engine to be able to render the particle that I am working with. |  | 4 | 2 | 2 | 4 |  |  | 4 | Manuel Diaz
As a programmer, I want to be able to load the assets created from the particle editor as well as any files needed for said assets. |  | 4 | 4 | 4 | 4 |  |  | 4 | Manuel Diaz
As a user, I want to have a clear and understandable Interface for my game |  | 12 | 8 | 12 | 12 |  |  | 12 | Charles Stoll
As a developer, I want an Event and Message system to send data easily to and between objects in game |  | 8 | 12 | 8 | 8 |  |  | 8 | Manuel Diaz
As a developer, I want to create an Object Hierarchy and systems to support them |  | 12 | 12 | 12 | 12 |  |  | 12 | Daniel Makin
As a developer, I want a Profiling tool to help find and reduce the number of bottlenecks in my code |  | 4 | 4 | 8 | 8 |  |  | 8 | Daniel Makin
As a user, I want a Gamer Profile system so I can save gameplay information that I can come back to |  | 12 | 12 | 12 | 12 |  |  | 12 | Manuel Diaz
As a developer, I want to submit an Art Request to insure my game looks awesomesauce |  | 4 | 4 | 4 | 2 |  |  | 4 | Daniel Makin
As a developer, I want a State Machine with an easy to understand interface so my teammates can change states based on their needs |  | 4 | 2 | 2 | 4 |  |  | 2 | Daniel Makin
As a user, I want have a deep and interesting combat system |  | 12 | 12 | 12 | 12 |  |  | 12 | Nick Kemner
As a user, I want to be able to move my units |  | 8 | 8 | 8 | 8 |  |  | 8 | Charles Stoll
As a programmer, I want an efficient and realistic collision system |  | 12 | 12 | 12 | 12 |  |  | 12 | Daniel Makin
You must insert rows above this point when adding user stories
Totals
|  | Charles Stoll | Daniel Makin | Nick Kemner | 0 | 0 | 0 | Totals
|  | 42 | 38 | 38 | 0 | 0 | 0 | 162
User Stories | Priority | Test cases
As an artist, I want a well thought-out and usable interface for my Animation editor. | high
Animation editors must use a tool strip and file menus.
All buttons and options of the animation editor must function.
As a designer, I want the buttons and tools in the Animation editor to be functional and my editor to fulfill the requirements of the class.
|  | Animation editors must at a minimum support having an Image rect, Collisions rect and anchor point in each frame. | Animation editors must at a minimum support having an Image rect, Collisions rect and anchor point in each frame. | Animation editors must at a minimum support having an Image rect, Collisions rect and anchor point in each frame. | Animation editors must at a minimum support having an Image rect, Collisions rect and anchor point in each frame. | Animation editors must at a minimum support having an Image rect, Collisions rect and anchor point in each frame. | Animation editors must at a minimum support having an Image rect, Collisions rect and anchor point in each frame.
|  | Animation editors must support manual editing of previously entered information (numeric up down for all the current info and properties) | Animation editors must support manual editing of previously entered information (numeric up down for all the current info and properties) | Animation editors must support manual editing of previously entered information (numeric up down for all the current info and properties) | Animation editors must support manual editing of previously entered information (numeric up down for all the current info and properties) | Animation editors must support manual editing of previously entered information (numeric up down for all the current info and properties) | Animation editors must support manual editing of previously entered information (numeric up down for all the current info and properties)
|  | Animation editors must have the ability to determine if an animation is looping or only plays once. | Animation editors must have the ability to determine if an animation is looping or only plays once. | Animation editors must have the ability to determine if an animation is looping or only plays once. | Animation editors must have the ability to determine if an animation is looping or only plays once. | Animation editors must have the ability to determine if an animation is looping or only plays once. | Animation editors must have the ability to determine if an animation is looping or only plays once.
|  | Animation editors must support tying game events with entering or exiting of animation frames | Animation editors must support tying game events with entering or exiting of animation frames | Animation editors must support tying game events with entering or exiting of animation frames | Animation editors must support tying game events with entering or exiting of animation frames | Animation editors must support tying game events with entering or exiting of animation frames | Animation editors must support tying game events with entering or exiting of animation frames
As a developer, I want my animation editor to be able to save and load my animations using relative paths.
|  | When the animation editor loads a previously saved file it must load associated files automatically as well (animations load the sprite sheet). | When the animation editor loads a previously saved file it must load associated files automatically as well (animations load the sprite sheet). | When the animation editor loads a previously saved file it must load associated files automatically as well (animations load the sprite sheet). | When the animation editor loads a previously saved file it must load associated files automatically as well (animations load the sprite sheet). | When the animation editor loads a previously saved file it must load associated files automatically as well (animations load the sprite sheet). | When the animation editor loads a previously saved file it must load associated files automatically as well (animations load the sprite sheet).
|  | Animation editors must be able to function with relative paths. The animation editor should be able to be run from anywhere and the animation editor should be able to load a file from anywhere without problem. | Animation editors must be able to function with relative paths. The animation editor should be able to be run from anywhere and the animation editor should be able to load a file from anywhere without problem. | Animation editors must be able to function with relative paths. The animation editor should be able to be run from anywhere and the animation editor should be able to load a file from anywhere without problem. | Animation editors must be able to function with relative paths. The animation editor should be able to be run from anywhere and the animation editor should be able to load a file from anywhere without problem. | Animation editors must be able to function with relative paths. The animation editor should be able to be run from anywhere and the animation editor should be able to load a file from anywhere without problem. | Animation editors must be able to function with relative paths. The animation editor should be able to be run from anywhere and the animation editor should be able to load a file from anywhere without problem.
|  | Animation editors must save and load binary files that will later be loaded by the game | Animation editors must save and load binary files that will later be loaded by the game | Animation editors must save and load binary files that will later be loaded by the game | Animation editors must save and load binary files that will later be loaded by the game | Animation editors must save and load binary files that will later be loaded by the game | Animation editors must save and load binary files that will later be loaded by the game
|  | Animation editors must save and load xml files that will used during the creation of assets (not loaded by the game) | Animation editors must save and load xml files that will used during the creation of assets (not loaded by the game) | Animation editors must save and load xml files that will used during the creation of assets (not loaded by the game) | Animation editors must save and load xml files that will used during the creation of assets (not loaded by the game) | Animation editors must save and load xml files that will used during the creation of assets (not loaded by the game) | Animation editors must save and load xml files that will used during the creation of assets (not loaded by the game)
|  | Animation editors must have the ability to save multiple animations per save file | Animation editors must have the ability to save multiple animations per save file | Animation editors must have the ability to save multiple animations per save file | Animation editors must have the ability to save multiple animations per save file | Animation editors must have the ability to save multiple animations per save file | Animation editors must have the ability to save multiple animations per save file
As a developer, I want an In-Tool engine to be able to render the animation that I am working with.
|  | Animation editors must contain a playback window that will allow you to see the animation play in real time using an anchor point | Animation editors must have the ability to save multiple animations per save file | Animation editors must have the ability to save multiple animations per save file | Animation editors must have the ability to save multiple animations per save file | Animation editors must have the ability to save multiple animations per save file | Animation editors must have the ability to save multiple animations per save file
As a programmer, I want to be able to load the assets created from the animation editor as well as any files needed for said asset.
Animation engines must be able to load and render animations previously created with the animation editor
When the animation engine loads an animation file it must load associated files automatically as well (animations load the sprite sheet).
Animation engines must use the collision information contained specified from the loaded animation file
Animation editors must throw events when entering frames specified from the loaded animation file
As an artist, I want a well thought-out and usable interface for my world editor.
|  | Tile editors must use a tool strip and file menus. | Tile editors must use a tool strip and file menus. | Tile editors must use a tool strip and file menus. | Tile editors must use a tool strip and file menus. | Tile editors must use a tool strip and file menus. | Tile editors must use a tool strip and file menus.
|  | All buttons and options of the tile editor must function. | All buttons and options of the tile editor must function. | All buttons and options of the tile editor must function. | All buttons and options of the tile editor must function. | All buttons and options of the tile editor must function. | All buttons and options of the tile editor must function.
As a designer, I want the buttons and tools in the world editor to be functional and my editor to fulfill the requirements of the class.
|  | Tile editors must support freehand drawing of tiles (drawing by clicking and dragging) | Tile editors must support freehand drawing of tiles (drawing by clicking and dragging) | Tile editors must support freehand drawing of tiles (drawing by clicking and dragging) | Tile editors must support freehand drawing of tiles (drawing by clicking and dragging) | Tile editors must support freehand drawing of tiles (drawing by clicking and dragging) | Tile editors must support freehand drawing of tiles (drawing by clicking and dragging)
|  | Tile editors must have the ability to create a map of an arbitrary size (rectangular shaped using whole numbers) | Tile editors must have the ability to create a map of an arbitrary size (rectangular shaped using whole numbers) | Tile editors must have the ability to create a map of an arbitrary size (rectangular shaped using whole numbers) | Tile editors must have the ability to create a map of an arbitrary size (rectangular shaped using whole numbers) | Tile editors must have the ability to create a map of an arbitrary size (rectangular shaped using whole numbers) | Tile editors must have the ability to create a map of an arbitrary size (rectangular shaped using whole numbers)
|  | Tile editors must have the ability to load in a custom tile set using any image (bmp or png) with tiles of any size (32x32, 8x8, 32x8) | Tile editors must have the ability to load in a custom tile set using any image (bmp or png) with tiles of any size (32x32, 8x8, 32x8) | Tile editors must have the ability to load in a custom tile set using any image (bmp or png) with tiles of any size (32x32, 8x8, 32x8) | Tile editors must have the ability to load in a custom tile set using any image (bmp or png) with tiles of any size (32x32, 8x8, 32x8) | Tile editors must have the ability to load in a custom tile set using any image (bmp or png) with tiles of any size (32x32, 8x8, 32x8) | Tile editors must have the ability to load in a custom tile set using any image (bmp or png) with tiles of any size (32x32, 8x8, 32x8)
|  | Tile editors must support at least one of the following: Multiple graphical layers, Layers for object spawning, paint bucket style area fill, or stamp style area fill) | Tile editors must support at least one of the following: Multiple graphical layers, Layers for object spawning, paint bucket style area fill, or stamp style area fill) | Tile editors must support at least one of the following: Multiple graphical layers, Layers for object spawning, paint bucket style area fill, or stamp style area fill) | Tile editors must support at least one of the following: Multiple graphical layers, Layers for object spawning, paint bucket style area fill, or stamp style area fill) | Tile editors must support at least one of the following: Multiple graphical layers, Layers for object spawning, paint bucket style area fill, or stamp style area fill) | Tile editors must support at least one of the following: Multiple graphical layers, Layers for object spawning, paint bucket style area fill, or stamp style area fill)
|  | Tile editors must support adding collision information onto the map in either Tile or dynamically drawn rect based collisions | Tile editors must support adding collision information onto the map in either Tile or dynamically drawn rect based collisions | Tile editors must support adding collision information onto the map in either Tile or dynamically drawn rect based collisions | Tile editors must support adding collision information onto the map in either Tile or dynamically drawn rect based collisions | Tile editors must support adding collision information onto the map in either Tile or dynamically drawn rect based collisions | Tile editors must support adding collision information onto the map in either Tile or dynamically drawn rect based collisions
|  | Tile editors must support tying game events with its supported collision types | Tile editors must support tying game events with its supported collision types | Tile editors must support tying game events with its supported collision types | Tile editors must support tying game events with its supported collision types | Tile editors must support tying game events with its supported collision types | Tile editors must support tying game events with its supported collision types
As a developer, I want my world editor to be able to save and load my maps using relative paths.
|  | When the tile editor loads a previously saved file it must load associated files automatically as well (maps load the tile sheet). | When the tile editor loads a previously saved file it must load associated files automatically as well (maps load the tile sheet). | When the tile editor loads a previously saved file it must load associated files automatically as well (maps load the tile sheet). | When the tile editor loads a previously saved file it must load associated files automatically as well (maps load the tile sheet). | When the tile editor loads a previously saved file it must load associated files automatically as well (maps load the tile sheet). | When the tile editor loads a previously saved file it must load associated files automatically as well (maps load the tile sheet).
|  | Tile editors must be able to function with relative paths. The tile editor should be able to be run from anywhere and the tile editor should be able to load a file from anywhere without problem. | Tile editors must be able to function with relative paths. The tile editor should be able to be run from anywhere and the tile editor should be able to load a file from anywhere without problem. | Tile editors must be able to function with relative paths. The tile editor should be able to be run from anywhere and the tile editor should be able to load a file from anywhere without problem. | Tile editors must be able to function with relative paths. The tile editor should be able to be run from anywhere and the tile editor should be able to load a file from anywhere without problem. | Tile editors must be able to function with relative paths. The tile editor should be able to be run from anywhere and the tile editor should be able to load a file from anywhere without problem. | Tile editors must be able to function with relative paths. The tile editor should be able to be run from anywhere and the tile editor should be able to load a file from anywhere without problem.
|  | Tile editors must save and load binary files that will later be loaded by the game | Tile editors must save and load binary files that will later be loaded by the game | Tile editors must save and load binary files that will later be loaded by the game | Tile editors must save and load binary files that will later be loaded by the game | Tile editors must save and load binary files that will later be loaded by the game | Tile editors must save and load binary files that will later be loaded by the game
As a developer, I want an In-Tool engine to be able to render the map that I am working with.
As a programmer, I want to be able to load the assets created from the world editor as well as any files needed for said assets.
|  | Tile engines must be able to load and render maps previously created with the tile editor | Tile engines must be able to load and render maps previously created with the tile editor | Tile engines must be able to load and render maps previously created with the tile editor | Tile engines must be able to load and render maps previously created with the tile editor | Tile engines must be able to load and render maps previously created with the tile editor | Tile engines must be able to load and render maps previously created with the tile editor
|  | Tile engines must cull tiles while rendering (only looping though and rendering the times currently on screen) | Tile engines must cull tiles while rendering (only looping though and rendering the times currently on screen) | Tile engines must cull tiles while rendering (only looping though and rendering the times currently on screen) | Tile engines must cull tiles while rendering (only looping though and rendering the times currently on screen) | Tile engines must cull tiles while rendering (only looping though and rendering the times currently on screen) | Tile engines must cull tiles while rendering (only looping though and rendering the times currently on screen)
|  | When the tile engine loads a map file it must load associated files automatically as well (maps load the tile sheet). | When the tile engine loads a map file it must load associated files automatically as well (maps load the tile sheet). | When the tile engine loads a map file it must load associated files automatically as well (maps load the tile sheet). | When the tile engine loads a map file it must load associated files automatically as well (maps load the tile sheet). | When the tile engine loads a map file it must load associated files automatically as well (maps load the tile sheet). | When the tile engine loads a map file it must load associated files automatically as well (maps load the tile sheet).
|  | Tile engines must use the collision information contained specified from the loaded map file | Tile engines must use the collision information contained specified from the loaded map file | Tile engines must use the collision information contained specified from the loaded map file | Tile engines must use the collision information contained specified from the loaded map file | Tile engines must use the collision information contained specified from the loaded map file | Tile engines must use the collision information contained specified from the loaded map file
|  | Tile editors must throw events when colliding with tiles or rects specified from the loaded map file | Tile editors must throw events when colliding with tiles or rects specified from the loaded map file | Tile editors must throw events when colliding with tiles or rects specified from the loaded map file | Tile editors must throw events when colliding with tiles or rects specified from the loaded map file | Tile editors must throw events when colliding with tiles or rects specified from the loaded map file | Tile editors must throw events when colliding with tiles or rects specified from the loaded map file
As an artist, I want a well thought-out and usable interface for my particle editor.
|  | Particle editors must use a tool strip and file menus. | Particle editors must use a tool strip and file menus. | Particle editors must use a tool strip and file menus. | Particle editors must use a tool strip and file menus. | Particle editors must use a tool strip and file menus. | Particle editors must use a tool strip and file menus.
|  | All buttons and options of the particle editor must function. | All buttons and options of the particle editor must function. | All buttons and options of the particle editor must function. | All buttons and options of the particle editor must function. | All buttons and options of the particle editor must function. | All buttons and options of the particle editor must function.
As a designer, I want the buttons and tools in the particle editor to be functional and my editor to fulfill the requirements of the class.
|  | Particle editors must support changing of a particles color, velocity, scale and rotation over time. | Particle editors must support changing of a particles color, velocity, scale and rotation over time. | Particle editors must support changing of a particles color, velocity, scale and rotation over time. | Particle editors must support changing of a particles color, velocity, scale and rotation over time. | Particle editors must support changing of a particles color, velocity, scale and rotation over time. | Particle editors must support changing of a particles color, velocity, scale and rotation over time.
|  | Particle editors must support emitting from within a determined range (rect, circle, line…) | Particle editors must support emitting from within a determined range (rect, circle, line…) | Particle editors must support emitting from within a determined range (rect, circle, line…) | Particle editors must support emitting from within a determined range (rect, circle, line…) | Particle editors must support emitting from within a determined range (rect, circle, line…) | Particle editors must support emitting from within a determined range (rect, circle, line…)
|  | Particle editors must support setting an use of DX Render State blend modes. | Particle editors must support setting an use of DX Render State blend modes. | Particle editors must support setting an use of DX Render State blend modes. | Particle editors must support setting an use of DX Render State blend modes. | Particle editors must support setting an use of DX Render State blend modes. | Particle editors must support setting an use of DX Render State blend modes.
|  | Particle editors must have the ability to determine if an effect is looping or only plays once. | Particle editors must have the ability to determine if an effect is looping or only plays once. | Particle editors must have the ability to determine if an effect is looping or only plays once. | Particle editors must have the ability to determine if an effect is looping or only plays once. | Particle editors must have the ability to determine if an effect is looping or only plays once. | Particle editors must have the ability to determine if an effect is looping or only plays once.
|  | Particle editors must have an option to randomize effects, with a configurable option to select which properties to modify. | Particle editors must have an option to randomize effects, with a configurable option to select which properties to modify. | Particle editors must have an option to randomize effects, with a configurable option to select which properties to modify. | Particle editors must have an option to randomize effects, with a configurable option to select which properties to modify. | Particle editors must have an option to randomize effects, with a configurable option to select which properties to modify. | Particle editors must have an option to randomize effects, with a configurable option to select which properties to modify.
As a developer, I want my particle editor to be able to save and load my particles using relative paths.
|  | When the particle editor loads a previously saved file it must load associated files automatically as well (particles effects load the particle image). | When the particle editor loads a previously saved file it must load associated files automatically as well (particles effects load the particle image). | When the particle editor loads a previously saved file it must load associated files automatically as well (particles effects load the particle image). | When the particle editor loads a previously saved file it must load associated files automatically as well (particles effects load the particle image). | When the particle editor loads a previously saved file it must load associated files automatically as well (particles effects load the particle image). | When the particle editor loads a previously saved file it must load associated files automatically as well (particles effects load the particle image).
|  | Particle editors must be able to function with relative paths. The particle editor should be able to be run from anywhere and the particle editor should be able to load a file from anywhere without problem. | Particle editors must be able to function with relative paths. The particle editor should be able to be run from anywhere and the particle editor should be able to load a file from anywhere without problem. | Particle editors must be able to function with relative paths. The particle editor should be able to be run from anywhere and the particle editor should be able to load a file from anywhere without problem. | Particle editors must be able to function with relative paths. The particle editor should be able to be run from anywhere and the particle editor should be able to load a file from anywhere without problem. | Particle editors must be able to function with relative paths. The particle editor should be able to be run from anywhere and the particle editor should be able to load a file from anywhere without problem. | Particle editors must be able to function with relative paths. The particle editor should be able to be run from anywhere and the particle editor should be able to load a file from anywhere without problem.
|  | Particle editors must save and load binary files that will later be loaded by the game. | Particle editors must save and load binary files that will later be loaded by the game. | Particle editors must save and load binary files that will later be loaded by the game. | Particle editors must save and load binary files that will later be loaded by the game. | Particle editors must save and load binary files that will later be loaded by the game. | Particle editors must save and load binary files that will later be loaded by the game.
|  | Particle editors must save and load xml files that will used during the creation of assets (not loaded by the game). | Particle editors must save and load xml files that will used during the creation of assets (not loaded by the game). | Particle editors must save and load xml files that will used during the creation of assets (not loaded by the game). | Particle editors must save and load xml files that will used during the creation of assets (not loaded by the game). | Particle editors must save and load xml files that will used during the creation of assets (not loaded by the game). | Particle editors must save and load xml files that will used during the creation of assets (not loaded by the game).
As a developer, I want an In-Tool engine to be able to render the particle that I am working with.
As a programmer, I want to be able to load the assets created from the particle editor as well as any files needed for said assets.
|  | Particle engines must be able to load and render particle effects previously created with the particle editor | Particle engines must be able to load and render particle effects previously created with the particle editor | Particle engines must be able to load and render particle effects previously created with the particle editor | Particle engines must be able to load and render particle effects previously created with the particle editor | Particle engines must be able to load and render particle effects previously created with the particle editor | Particle engines must be able to load and render particle effects previously created with the particle editor
|  | When the particle engine loads a particle effect file it must load associated files automatically as well (particles effects load the particle image). | When the particle engine loads a particle effect file it must load associated files automatically as well (particles effects load the particle image). | When the particle engine loads a particle effect file it must load associated files automatically as well (particles effects load the particle image). | When the particle engine loads a particle effect file it must load associated files automatically as well (particles effects load the particle image). | When the particle engine loads a particle effect file it must load associated files automatically as well (particles effects load the particle image). | When the particle engine loads a particle effect file it must load associated files automatically as well (particles effects load the particle image).
|  | Particle engines must support positioning particle effects on moving game objects | Particle engines must support positioning particle effects on moving game objects | Particle engines must support positioning particle effects on moving game objects | Particle engines must support positioning particle effects on moving game objects | Particle engines must support positioning particle effects on moving game objects | Particle engines must support positioning particle effects on moving game objects
|  | Particle engines must use the DX blend modes specified from the loaded particle file | Particle engines must use the DX blend modes specified from the loaded particle file | Particle engines must use the DX blend modes specified from the loaded particle file | Particle engines must use the DX blend modes specified from the loaded particle file | Particle engines must use the DX blend modes specified from the loaded particle file | Particle engines must use the DX blend modes specified from the loaded particle file
As a user, I want to have a clear and understandable Interface for my game
|  | The game must have a fully functional standard menu system (main menu, options menu, pause menu, how to play screens) | The game must have a fully functional standard menu system (main menu, options menu, pause menu, how to play screens) | The game must have a fully functional standard menu system (main menu, options menu, pause menu, how to play screens) | The game must have a fully functional standard menu system (main menu, options menu, pause menu, how to play screens) | The game must have a fully functional standard menu system (main menu, options menu, pause menu, how to play screens) | The game must have a fully functional standard menu system (main menu, options menu, pause menu, how to play screens)
|  | The game must be fully navigable using nothing but the keyboard | The game must be fully navigable using nothing but the keyboard | The game must be fully navigable using nothing but the keyboard | The game must be fully navigable using nothing but the keyboard | The game must be fully navigable using nothing but the keyboard | The game must be fully navigable using nothing but the keyboard
|  | The game must be fully navigable using nothing but a gamepad/controller | The game must be fully navigable using nothing but a gamepad/controller | The game must be fully navigable using nothing but a gamepad/controller | The game must be fully navigable using nothing but a gamepad/controller | The game must be fully navigable using nothing but a gamepad/controller | The game must be fully navigable using nothing but a gamepad/controller
|  | The game must use a bitmap or other texture based system to display text to the screen. Bitmapped fonts must support kerning. | The game must use a bitmap or other texture based system to display text to the screen. Bitmapped fonts must support kerning. | The game must use a bitmap or other texture based system to display text to the screen. Bitmapped fonts must support kerning. | The game must use a bitmap or other texture based system to display text to the screen. Bitmapped fonts must support kerning. | The game must use a bitmap or other texture based system to display text to the screen. Bitmapped fonts must support kerning. | The game must use a bitmap or other texture based system to display text to the screen. Bitmapped fonts must support kerning.
|  | The interface is easy to understand and use | The interface is easy to understand and use | The interface is easy to understand and use | The interface is easy to understand and use | The interface is easy to understand and use | The interface is easy to understand and use
|  | All pieces of the interface work | All pieces of the interface work | All pieces of the interface work | All pieces of the interface work | All pieces of the interface work | All pieces of the interface work
As a developer, I want an Event and Message system to send data easily to and between objects in game
|  | The game must be able to demonstrate a messaging system | The game must be able to demonstrate a messaging system | The game must be able to demonstrate a messaging system | The game must be able to demonstrate a messaging system | The game must be able to demonstrate a messaging system | The game must be able to demonstrate a messaging system
|  | The game must be able to demonstrate an event system | The game must be able to demonstrate an event system | The game must be able to demonstrate an event system | The game must be able to demonstrate an event system | The game must be able to demonstrate an event system | The game must be able to demonstrate an event system
|  | Both systems can be demonstrated in-game | Both systems can be demonstrated in-game | Both systems can be demonstrated in-game | Both systems can be demonstrated in-game | Both systems can be demonstrated in-game | Both systems can be demonstrated in-game
As a developer, I want to create an Object Hierarchy and systems to support them
|  | The game must have a system built to create and manage game objects | The game must have a system built to create and manage game objects | The game must have a system built to create and manage game objects | The game must have a system built to create and manage game objects | The game must have a system built to create and manage game objects | The game must have a system built to create and manage game objects
|  | The game must contain all core game objects with base functionality | The game must contain all core game objects with base functionality | The game must contain all core game objects with base functionality | The game must contain all core game objects with base functionality | The game must contain all core game objects with base functionality | The game must contain all core game objects with base functionality
|  | The game must support collision between game objects (rect to rect collision at a minimum) | The game must support collision between game objects (rect to rect collision at a minimum) | The game must support collision between game objects (rect to rect collision at a minimum) | The game must support collision between game objects (rect to rect collision at a minimum) | The game must support collision between game objects (rect to rect collision at a minimum) | The game must support collision between game objects (rect to rect collision at a minimum)
|  | The game demonstrates the ability to handle multiple objects on screen | The game demonstrates the ability to handle multiple objects on screen | The game demonstrates the ability to handle multiple objects on screen | The game demonstrates the ability to handle multiple objects on screen | The game demonstrates the ability to handle multiple objects on screen | The game demonstrates the ability to handle multiple objects on screen
As a developer, I want a Profiling tool to help find and reduce the number of bottlenecks in my code
|  | A debug tool must be created that will profile functions for the duration it takes them to execute. | A debug tool must be created that will profile functions for the duration it takes them to execute. | A debug tool must be created that will profile functions for the duration it takes them to execute. | A debug tool must be created that will profile functions for the duration it takes them to execute. | A debug tool must be created that will profile functions for the duration it takes them to execute. | A debug tool must be created that will profile functions for the duration it takes them to execute.
|  | The Code profiler must use a high resolution timer. | The Code profiler must use a high resolution timer. | The Code profiler must use a high resolution timer. | The Code profiler must use a high resolution timer. | The Code profiler must use a high resolution timer. | The Code profiler must use a high resolution timer.
|  | The code profiler must be able to profile multiple functions at once. | The code profiler must be able to profile multiple functions at once. | The code profiler must be able to profile multiple functions at once. | The code profiler must be able to profile multiple functions at once. | The code profiler must be able to profile multiple functions at once. | The code profiler must be able to profile multiple functions at once.
|  | The code profiler must output to a file the highest lowest average and a list of all the times the function was profiled. | The code profiler must output to a file the highest lowest average and a list of all the times the function was profiled. | The code profiler must output to a file the highest lowest average and a list of all the times the function was profiled. | The code profiler must output to a file the highest lowest average and a list of all the times the function was profiled. | The code profiler must output to a file the highest lowest average and a list of all the times the function was profiled. | The code profiler must output to a file the highest lowest average and a list of all the times the function was profiled.
|  | The data compiled from the run is presented to the user clearly | The data compiled from the run is presented to the user clearly | The data compiled from the run is presented to the user clearly | The data compiled from the run is presented to the user clearly | The data compiled from the run is presented to the user clearly | The data compiled from the run is presented to the user clearly
As a user, I want a Gamer Profile system so I can save gameplay information that I can come back to
|  | The game must contain a Gamer Profile saving system (save slot system containing new game load game delete game at a minimum) | The game must contain a Gamer Profile saving system (save slot system containing new game load game delete game at a minimum) | The game must contain a Gamer Profile saving system (save slot system containing new game load game delete game at a minimum) | The game must contain a Gamer Profile saving system (save slot system containing new game load game delete game at a minimum) | The game must contain a Gamer Profile saving system (save slot system containing new game load game delete game at a minimum) | The game must contain a Gamer Profile saving system (save slot system containing new game load game delete game at a minimum)
|  | Profiles can be created, modified, and deleted | Profiles can be created, modified, and deleted | Profiles can be created, modified, and deleted | Profiles can be created, modified, and deleted | Profiles can be created, modified, and deleted | Profiles can be created, modified, and deleted
As a developer, I want to submit an Art Request to insure my game looks awesomesauce
|  | An asset request must be filled out and approved by both your AP and the art director | An asset request must be filled out and approved by both your AP and the art director | An asset request must be filled out and approved by both your AP and the art director | An asset request must be filled out and approved by both your AP and the art director | An asset request must be filled out and approved by both your AP and the art director | An asset request must be filled out and approved by both your AP and the art director
As a developer, I want a State Machine with an easy to understand interface so my teammates can change states based on their needs
|  | The game must be able to set to hold and run the current game state and support changing from one game state to another. | An asset request must be filled out and approved by both your AP and the art director | An asset request must be filled out and approved by both your AP and the art director | An asset request must be filled out and approved by both your AP and the art director | An asset request must be filled out and approved by both your AP and the art director | An asset request must be filled out and approved by both your AP and the art director
As a user, I want have a deep and interesting combat system
|  | I want to be able to attack enemy units | I want to be able to attack enemy units | I want to be able to attack enemy units | I want to be able to attack enemy units | I want to be able to attack enemy units | I want to be able to attack enemy units
|  | I want to be able to use the medic's heal ability | I want to be able to use the medic's heal ability | I want to be able to use the medic's heal ability | I want to be able to use the medic's heal ability | I want to be able to use the medic's heal ability | I want to be able to use the medic's heal ability
|  | I want to be able to kill enemies | I want to be able to kill enemies | I want to be able to kill enemies | I want to be able to kill enemies | I want to be able to kill enemies | I want to be able to kill enemies
|  | I want to be able to attack together or seperately | I want to be able to attack together or seperately | I want to be able to attack together or seperately | I want to be able to attack together or seperately | I want to be able to attack together or seperately | I want to be able to attack together or seperately
|  | I want for player units to be able to be incapacitated | I want for player units to be able to be incapacitated | I want for player units to be able to be incapacitated | I want for player units to be able to be incapacitated | I want for player units to be able to be incapacitated | I want for player units to be able to be incapacitated
As a user, I want to be able to move my units
|  | I want to be able to select one or multiple of my units | I want to be able to select one or multiple of my units | I want to be able to select one or multiple of my units | I want to be able to select one or multiple of my units | I want to be able to select one or multiple of my units | I want to be able to select one or multiple of my units
|  | I want to move intuitively around the map, following a pathing algorithm | I want to move intuitively around the map, following a pathing algorithm | I want to move intuitively around the map, following a pathing algorithm | I want to move intuitively around the map, following a pathing algorithm | I want to move intuitively around the map, following a pathing algorithm | I want to move intuitively around the map, following a pathing algorithm
|  | I want to be able to stop my units if they are moving | I want to be able to stop my units if they are moving | I want to be able to stop my units if they are moving | I want to be able to stop my units if they are moving | I want to be able to stop my units if they are moving | I want to be able to stop my units if they are moving
|  | I want to be able to stop and attack if enemies are nearby | I want to be able to stop and attack if enemies are nearby | I want to be able to stop and attack if enemies are nearby | I want to be able to stop and attack if enemies are nearby | I want to be able to stop and attack if enemies are nearby | I want to be able to stop and attack if enemies are nearby
As a programmer, I want an efficient and realistic collision system
|  | I want units to not go through solid objects | I want units to not go through solid objects | I want units to not go through solid objects | I want units to not go through solid objects | I want units to not go through solid objects | I want units to not go through solid objects
|  | I want units to check collisions based on object type | I want units to check collisions based on object type | I want units to check collisions based on object type | I want units to check collisions based on object type | I want units to check collisions based on object type | I want units to check collisions based on object type
|  | I want units to path around solid objects | I want units to path around solid objects | I want units to path around solid objects | I want units to path around solid objects | I want units to path around solid objects | I want units to path around solid objects
|  | I want projectiles to collide and do appropriate effects | I want projectiles to collide and do appropriate effects | I want projectiles to collide and do appropriate effects | I want projectiles to collide and do appropriate effects | I want projectiles to collide and do appropriate effects | I want projectiles to collide and do appropriate effects

## S3 Allocation
Sprint 1 Allocation |  | Bids | [5 empty] | Finals
User Stories |  | Ben Bair | Daniel Makin | Nick Kemner | 0 | 0 | 0 | Agreed upon bid | Owner
As a player, I want to have an easy to navigate menu system with all options available |  | 8 | 8 | 4 |  |  |  | 8 | Ben Bair
As a player, I want a screen that I have to press start to continue |  | 2 | 2 | 2 |  |  |  | 2 | Ben Bair
As a player, I want a summary of my accomplishments of the level |  | 2 | 2 | 2 |  |  |  | 2 | Ben Bair
As a player, I want to be able to save my progress in separate profiles so I may load them up later |  | 4 | 4 | 4 |  |  |  | 4 | Nick Kemner
As a player, I want to be able to use the in game interface effectively |  | 4 | 4 | 4 |  |  |  | 4 | Ben Bair
As a player, I want to be able to use the full range of attacks available to me |  | 12 | 12 | 12 |  |  |  | 12 | Nick Kemner
As a player, I want to be able to control all of the types of units available to me |  | 4 | 4 | 4 |  |  |  | 4 | Nick Kemner
As a player, I want to be able to collect and use all of the powerups available to me |  | 8 | 8 | 8 |  |  |  | 8 | Daniel Makin
As a player, I want to be able to change the full range of hotkeys |  | 4 | 4 | 4 |  |  |  | 4 | Ben Bair
As a player, I want to be able to use the mouse to select and control the units, pick up items and control the camera |  | 4 | 4 | 4 |  |  |  | 4 | Daniel Makin
As a player, I want to be able play all of the levels |  | 12 | 12 | 12 |  |  |  | 12 | Nick Kemner
As a programmer, I want to have a system to play dialogue at the right time |  | 8 | 8 | 8 |  |  |  | 8 | Daniel Makin
As a tester, I want to be able to enter a cheat code to further me in the game |  | 2 | 2 | 2 |  |  |  | 2 | Ben Bair
As a player, I want to be able to complete levels or be able to die and have to start over |  | 2 | 2 | 2 |  |  |  | 2 | Nick Kemner
As a developer, I want characters to behave differently using different states to control them |  | 4 | 4 | 4 |  |  |  | 4 | Ben Bair
As a player, I want enemies to make informed decisions |  | 12 | 12 | 12 |  |  |  | 12 | Daniel Makin
As a player, when I'm not controlling the survivors, I want them to make basic decisions based on their type |  | 8 | 8 | 8 |  |  |  | 8 | Daniel Makin
As a player, I want bosses to use their abilities to make challenging battles |  | 8 | 8 | 8 |  |  |  | 8 | Daniel Makin
As a player, I want all units to avoid solid objects in order to reach their destination |  | 12 | 12 | 12 |  |  |  | 12 | Ben Bair
As a player, I want to hear background music and sound effects all throughout the game |  | 4 | 4 | 4 |  |  |  | 4 | Nick Kemner
As a player, I want to be able to save progress throughout the levels |  | 2 | 2 | 2 |  |  |  | 2 | Nick Kemner
As a developer, I want to have all of my assets in place |  | 2 | 2 | 2 |  |  |  | 2 | Ben Bair
You must insert rows above this point when adding user stories
Totals
|  | Ben Bair | Daniel Makin | Nick Kemner | 0 | 0 | 0 | Totals
|  | 40 | 48 | 40 | 0 | 0 | 0 | 128
User Stories | Priority | Test cases
As a player, I want to have an easy to navigate menu system with all options available
Is it easy to navigate?
Are all options available?
Is it navigable completely by keyboard?
As a player, I want a screen that I have to press start to continue
As a player, I want a summary of my accomplishments of the level
Are the following shown:
overall score
kills
who survived
overview of story
items acquired
name of the next level
As a player, I want to be able to save my progress in separate profiles so I may load them up later
can I load correctly?
can I save correctly?
are the profiles discernible by name or otherwise?
do the profiles show game progress and information?
As a player, I want to be able to use the in game interface effectively
are tooltips shown?
do all buttons work correctly?
does the mini map work correctly?
As a player, I want to be able to use the full range of attacks available to me
are all 3 of each characters abilities able to be used, if unlocked?
As a player, I want to be able to control all of the types of units available to me
are all 4 player controllable units able to be controlled properly?
As a player, I want to be able to collect and use all of the powerups available to me
are all the powerups functional and in game?
can you pick up powerups?
if passive, are the abilities in effect?
if active, are they able to be toggled?
As a player, I want to be able to change the full range of hotkeys
are non system keys able to be mapped by the user?
do they save on program exit?
do they load on program start?
As a player, I want to be able to use the mouse to select and control the units, pick up items and control the camera
As a player, I want to be able play all of the levels
do all of the levels have objectives to complete?
As a programmer, I want to have a system to play dialogue at the right time
As a tester, I want to be able to enter a cheat code to further me in the game
"dog" - Activates godmode where player units don't take damage, and can't die
"gogo" - Cooldowns are locked to be always ready for player units.
"stats" - Adds +10 to all stats of player units.
"bored" - Skip the current level.
As a player, I want to be able to complete levels or be able to die and have to start over
does a death send you to the beginning of the level or to the last checkpoint?
does the level actually complete and send to tally screen on completion?
As a developer, I want characters to behave differently using different states to control them
As a player, I want enemies to make informed decisions
do enemies attack players if in range?
do they follow players if they're out of combat range but in sight?
do they perform some sort of last measure if they are about to die? (either run or strong attack)
As a player, when I'm not controlling the survivors, I want them to make basic decisions based on their type
As a player, I want bosses to use their abilities to make challenging battles
do boss abilities work?
do bosses attack players in range?
do bosses use abilities intelligently to defeat player?
As a player, I want all units to avoid solid objects in order to reach their destination
do units walk around solid objects?
do units take an efficient path to their destination?
As a player, I want to hear background music and sound effects all throughout the game
does the background music play?
do sound effects play?
As a player, I want to be able to save progress throughout the levels
do the checkpoints give indication of save?
do the checkpoints save the progress correctly?
As a developer, I want to have all of my assets in place
are all assets in the correct folders?
are all assets named properly?
do all assets load properly? (i.e. images power of 2)

## S4 Allocation
Sprint 1 Allocation |  | Bids | [6 empty] | Finals
User Stories |  | Charles Stoll | Daniel Makin | Nick Kemner | 0 | 0 | 0 |  | Agreed upon bid | Owner
As a developer, I want the game to generate pathing data faster. |  | 12 | 12 | 12 |  |  |  |  | 12 | Charles Stoll | 6%
As a player, I want pathing to be more efficient and natural looking. |  | 12 | 12 | 12 |  |  |  |  | 12 | Daniel Makin
As a player, I want balanced unit stats. |  | 8 | 4 | 8 |  |  |  |  | 8 | Nick Kemner
As a player, I want balanced unit ability durations and cooldowns. |  | 4 | 4 | 4 |  |  |  |  | 4 | Nick Kemner
As a player, I want to see unit ability durations and cooldown times. |  | 8 | 8 | 8 |  |  |  |  | 8 | Nick Kemner
As a player, I want the button image for the ability to show the ability. |  | 2 | 2 | 2 |  |  |  |  | 2 | Nick Kemner
As a player, I want inventory items to have unique images. |  | 2 | 2 | 2 |  |  |  |  | 2 | Daniel Makin
As a player, I want to be able to create different profiles and save to them. |  | 4 | 4 | 4 |  |  |  |  | 4 | Daniel Makin
As a player, I want all of the units to have appropriate animation. |  | 8 | 8 | 8 |  |  |  | ` | 8 | Nick Kemner
As a player, I want visually interesting maps. |  | 12 | 12 | 12 |  |  |  |  | 12 | Charles Stoll | 35%
As a player, I want maps with interesting layouts. |  | 4 | 4 | 4 |  |  |  |  | 4 | Charles Stoll | 33%
As a player, I want to see an effect when a unit fires instead of a white line. |  | 8 | 8 | 8 |  |  |  |  | 8 | Daniel Makin
As a developer, I don't want to use drawline. |  | 2 | 2 | 2 |  |  |  |  | 2 | Daniel Makin
As a player, I want to face a boss at the end of every level. |  | 12 | 12 | 12 |  |  |  |  | 12 | Daniel Makin
As a player, I want to be able to install this game. |  | 2 | 2 | 2 |  |  |  |  | 2 | Daniel Makin
As a developer, I want to be able to run the game at 60 fps. |  | 2 | 2 | 2 |  |  |  |  | 2 | Charles Stoll | 0%
As a developer, I want my game to run in release mode. |  | 2 | 2 | 2 |  |  |  |  | 2 | Nick Kemner
As a player, I want tooltips that display specific information. |  | 8 | 8 | 8 |  |  |  |  | 8 | Nick Kemner
As a player, I want to see a loading screen whenever the game is loading something. |  | 4 | 4 | 4 |  |  |  |  | 4 | Charles Stoll | 95%
As a developer, I want my game to meet TRC Requirements. |  | 12 | 12 | 12 |  |  |  |  | 12 | Charles Stoll | 20%
You must insert rows above this point when adding user stories
Totals
|  | Charles Stoll | Daniel Makin | Nick Kemner | 0 | 0 | 0 |  | Totals
|  | 46 | 42 | 40 | 0 | 0 | 0 |  | 128
User Stories | Priority | Test cases
As a developer, I want the game to generate pathing data faster.
does it load levels quickly and correctly?
does it load premade pathing data?
As a player, I want pathing to be more efficient and natural looking.
do units not walk into blocked areas?
do units take an effiecient path of some sort?
As a player, I want balanced unit stats.
As a player, I want balanced unit ability durations and cooldowns.
As a player, I want to see unit ability durations and cooldown times.
does it show the duration and cooldown graphically and clearly?
does it show a graphical effect on the unit?
As a player, I want the button image for the ability to show the ability.
does it integrate an art effect?
As a player, I want inventory items to have unique images.
does it integrate an art effect?
As a player, I want to be able to create different profiles and save to them.
can the profile be named and associated with specific save files?
can the profile be accessed from the main menu?
As a player, I want all of the units to have appropriate animation.
As a player, I want visually interesting maps.
is the first map remade with more detail and a different tile set?
is the second map remade with more detail and a different tile set?
is the third map a recreation of ROG Captain's Log?
As a player, I want maps with interesting layouts.
As a player, I want to see an effect when a unit fires instead of a white line.
does it use particles?
As a developer, I don't want to use drawline.
As a player, I want to face a boss at the end of every level.
do bosses use abilites?
do bosses have good ai?
As a player, I want to be able to install this game.
do we have a successful install file?
As a developer, I want to be able to run the game at 60 fps.
As a developer, I want my game to run in release mode.
As a player, I want tooltips that display specific information.
do they specify what abilities and items do, including name, effect, cooldown and duration
As a developer, I want my game to meet TRC Requirements.
does the game have 3 save slots?
is saving available from an in game menu?
does the main menu include an option to show a series of screens that tell the player what his/her main objectives are, and how to use the controls?
does menu options include a credits option?
does the game have music in all portions?
do all actions have a sound effect associated with them?
does alt + tab pause game?
does the game save/load in binary?
does it meet all trc requirements?